## Project Timeline
vnTeam3-ML-Project Plan
PROJECT TITLE |  | ML- Hands-on project
PROJECT MANAGER |  | Huynh Ba Dieu
PHASE |  |  | DETAILS
| PROJECT WEEK: |  | Enter the date of the first Monday of each month --> | Assigned Tasks | Status
1 | Project Initiation |  | Team setting, | Team | TRUE
|  |  | Meeting with mentor | Team | TRUE
|  |  | Discuss & Dataset selection | Team | TRUE
2 | Research & practices (AWS, EC2, Lambda, API, S3, ...) and Explore the Dataset Streamlit app |  | - Each team members study & practices with AWS and services | Team/ Individual | TRUE
|  |  | - Setting up Git and intergrate to EC2 | Thuan+Tinh | TRUE
|  |  | - Discuss and Pick the data set relevant to the analysis e.g., regression, classification | Team
|  |  | -Interpret the behavior of the model based on hyperparameter tuning | Team
|  |  | Meeting with mentor | Team | on Thursday
3 | Project Execution |  | - High-level design of the platform | Man
|  |  | - ML pipeline including data cleansing, data processing, data ingestion scripts. | Trinh, Dieu
|  |  | - Web application to render the analysis and prediction output | Sanh, Trinh
|  |  | - AWS service monitoring and management scripts to achieve optimization | Tinh, Thuan
4 | Test and Demotration |  | - Test the system with different dataset | Man, Dieu
|  |  | - Evaluation | Team
|  |  | - Demo and Presentation | Team
5 | Project Close |  | - Lesson learned | Team
|  |  | - Discussion | Team
|  |  | - Report | Man